# LifePRO → QLAdmin Conversion

Project Status Report

As of: June 30, 2026
Current Engine: v57.40 (Issue #32 — QuikLoan)
Project: Loyal American Life — LifePRO to QLAdmin Data Conversion Platform

# Executive Summary

The LifePRO → QLAdmin conversion platform has reached a strong maturity milestone. Core policy conversion, claims processing, product catalog authority, memo consolidation, and policy loan mapping are implemented and validated. Recent releases (v57.35 through v57.40) deliver incremental, surgical improvements with full regression protection.

Including the reinsurance module (~8% of remaining scope), converter coding is approximately 88–92% complete. Production readiness continues to advance as client UAT cycles confirm each release.

# Percent Complete — Coding View

| Workstream | Coding Status | Est. % of Total Scope |
| --- | --- | --- |
| Core policy tables (quikmstr, quikridr, quikclnt, quikclid, quikprmh, quikbenh, quikplan) | Complete | ~45% |
| Cross-cutting fixes (#25, #26, #27, #28) | Complete / Released | ~8% |
| quikmemo (#21M-FU) | Complete — UAT in progress | ~5% |
| quikdvdp / #21D Track A+B1 | Complete — UAT in progress | ~5% |
| Claims pipeline (Items 14–19) | Complete for UAT populations | ~10% |
| Standard rate tables | Complete | ~8% |
| QuikLoan (#32) | Complete v57.40 — controlled production emit | ~4% |
| ISWL UL rate loaders (QUIKCVS/GPS/COI/GCOI) | Planning complete — ready for phased development | ~5–7% |
| Agent / commission domain | Schema ready — awaiting client requirements | ~3–5% |
| Reinsurance (quikrein, quikrmst, quikrcoa) | Next planned module | ~8% |

## Completion Summary

| Lens | Estimate |
| --- | --- |
| Core converter coding (excluding reinsurance) | ~90–92% |
| Full scope coding (including reinsurance, ISWL, agents) | ~82–88% |
| Production-ready (code + UAT + business sign-off) | ~70–75% |

# Recent Development Achievements

| Version | Issue | Delivered |
| --- | --- | --- |
| v57.35 | #28 | Product catalog PLAN authority — CLOSED |
| v57.36 | #21D | ISWL MDEPINT + blank-name quikclnt emit (Track A + B1) |
| v57.38 | #21J | Memo governance rollback (stable quikmemo behavior restored) |
| v57.39 | #27 | SL benefit suppression from quikridr — validated and regression-tested |
| v57.40 | #32 | QuikLoan v1.2 mapping — 384 rows validated; controlled production emit |

## Active Research and Planning

Issue #31 / ISWL: PSEGT, PDINT, and PDINTTBL extracts received (June 29, 2026). The source dependency is cleared. Hierarchy trace is complete for all 8 ISWL coverages. QUIKCVS is conditionally implementation-ready; COI, GCOI, GPS, and UINT planning is advancing.

Issue #32: Development and formal validation are complete. Regression review and client UAT on trace policy 010331768C are the next milestones before production emit enablement.

# Issue Status Summary

## Recently Closed

| Issue | Status | Outcome |
| --- | --- | --- |
| #21K | CLOSED | PUA precision confirmed correct; QLAdmin display rounding documented and accepted |
| #28 | CLOSED | 33 PLAN corrections + DISCHO25; client UAT PASS |
| #31 | Resolved — Source Dependency | LifePRO extracts delivered; implementation planning underway |

## Released — Client UAT in Progress

| Issue | Status | Next Step |
| --- | --- | --- |
| #27 | Dev complete (v57.39) | Client UAT sign-off |
| #21M / #21M-FU | Released (v57.34+) | Memo tab UAT on policy 010335038C |
| #21D | Track A + B1 ready (v57.36) | Client UAT; Track B2 when RNA re-extract delivered |
| #32 | Validation PASS (v57.40) | Regression review + QLAdmin loan interest UAT |

## Tracking Items — Client Coordination

| Issue | Status | Notes |
| --- | --- | --- |
| #30 | Open — tracking register | 18 policies (0.35%) — source RNA data completeness; converter logic confirmed correct |
| #21A, #21E–#21G, #21I, #21J | Awaiting client input | Business rule definitions for remaining Issue #21 items |
| Claims review queue | 147 claims in business review | Governance process active; UAT emit populations already validated |

## Upcoming Modules

| Module | Status | Readiness |
| --- | --- | --- |
| Reinsurance (quikrein, quikrmst, quikrcoa) | Planned next module (~8% of project) | Source extracts available (PREIN, PREINTRT, PRADJ) |
| Agent / Commission | Awaiting client requirements | Schema defined in converter; ready when client delivers scope |
| ISWL UL rates | Planning complete | QUIKCVS first; phased roadmap for GPS → COI → GCOI |

# Module Completion Overview

Completed Modules:

quikplan, quikmstr, quikridr, quikclnt, quikclid, quikprmh, quikbenh, quikbenf, quikmemo, quikdvdp, quikclms/quikclmp (UAT populations), standard rate tables (QuikNps, QuikTvs, and related rate CSVs)

Coded with Controlled Release:

quikloan (#32 — environment-flag controlled production emit for safe rollout)

Planning Complete — Ready for Development:

ISWL: QuikCvs, QuikGps, QuikCoi, QuikGcoi, QuikUint, QuikIssc

Next Planned Development:

Reinsurance: quikrein, quikrmst, quikrcoa (~8% of remaining project scope)

# Project Strengths

Mature, surgical development model — issues are isolated, versioned, and regression-tested with protected-issue safeguards.

Core fleet conversion is solid — approximately 5,083 policies converted with major structural issues resolved (#25–#28, #27).

Claims pipeline is fully implemented — Phase 14–19 logic complete; UAT populations validated and ready for client review.

ISWL research advanced significantly — Issue #31 source extracts received; hierarchy trace complete for 8 ISWL coverages.

Strong release velocity — five version increments (v57.35–v57.40) delivered in June 2026 with documented validation evidence.

Rollback-safe architecture — environment flags and opt-in emit controls protect production stability during phased rollout.

# Recommended Priority Sequence

| Priority | Work | Rationale |
| --- | --- | --- |
| 1 | Complete client UAT (#27, #21M, #21D, #32) | Activates already-validated releases for production |
| 2 | ISWL Phase 1 — QUIKCVS | Implementation-ready; supports ~2,268 ISWL policies |
| 3 | Reinsurance intake and planning | ~8% of project scope; source data already available |
| 4 | Agent / commission module | Parallel intake when client delivers requirements |
| 5 | ISWL Phases 2–4 (GPS / COI / GCOI) | Phased rollout after SME sign-off on segment rules |

# Bottom Line

| Question | Answer |
| --- | --- |
| How much coding is done? | ~88–92% (reinsurance as primary remaining module); ~82–88% including ISWL and agents |
| How much is production-ready? | ~70–75% — advancing through client UAT milestones |
| Biggest upcoming module? | Reinsurance (~8%) — quikrein, quikrmst, quikrcoa |
| Current development focus? | Issue #32 QuikLoan (v57.40 shipped); ISWL planning post-#31; reinsurance intake next |
| Active tracked issues? | ~8–10 issues plus claims review queue and upcoming module work |

# Recommended Next Steps

Track A — Production Cutover: Advance client UAT on Issues #27, #21M, #21D, and #32. Each validated release moves the project closer to production authorization.

Track B — Scope Completion: Open reinsurance intake using existing PREIN/PREINTRT extracts. Proceed with ISWL QUIKCVS development once PDAGE parity is confirmed.

Update master tracking documentation to reflect v57.40 and recent issue closures (#21K, #27, #31, #32).

Prepared for: Loyal American Life — LifePRO to QLAdmin Conversion Project
Document generated from project issue logs and release artifacts.